## Group
Part # | Deliverable | SubTask/Content (Based on Project Details) | Description/ Suggestions | Due Date (Expected Date to finish) | Deadline | Assignee / Volunteer | Status | Team Comments | Deliverable Comments
1 | Project Proposal |  | Approval document | 2026-04-24 | 2026-04-26 | Tom Jason D. Umali | Completed | Project proposal document approved and submitted.
| Cover Page & Table of Contents |  |  | 2026-04-24 |  | Tom Jason D. Umali | Completed | Project proposal document approved and submitted.
| Executive Summary |  |  | 2026-04-24 |  | Tom Jason D. Umali | Completed | Project proposal document approved and submitted.
2 | Company Background |  | Profile, AS-IS, business case | 2026-04-24 | 2026-04-26 | Jade Allen Rubico | Completed | Company background and AS-IS architecture completed.
| Company Profile | Name |  | 2026-04-24 |  | Jade Allen Rubico | Completed | Company background and AS-IS architecture completed.
|  | Industry |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Size |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Locations |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Organizational Structure | Diagram/Description | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Current IT Environment |  | 2026-04-24 |  | Jade Allen Rubico | Completed
| Current State Assessment (AS-IS) | Process Descriptions |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Pain Points (minimum 10 with impact) | Table | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Technology Landscape |  | 2026-04-24 |  | Jade Allen Rubico | Completed
| Business Case | Strategic Objectives |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Quantified Benefits |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Cost of Inaction |  | 2026-04-24 |  | Jade Allen Rubico | Completed
| Solution Vision | High-level Description |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Key Capabilities |  | 2026-04-24 |  | Jade Allen Rubico | Completed
|  | Success Criteria (KPIs) |  | 2026-04-24 |  | Jade Allen Rubico | Completed
3 | TO-BE Business Architecture |  | Capabilities, value streams, BPMN | 2026-05-01 | 2026-05-03 | Jade Allen Rubico | Completed | TO-BE Business Architecture completed and document uploaded.
| Business Capability Model | Capability Map (Level 1) | Diagrams | 2026-05-01 |  | Jade Allen Rubico | Completed | TO-BE Business Architecture completed and document uploaded.
|  | Capability Map (Level 2) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Capability Map (Level 3) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Heat Map | Diagrams | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Gap Analysis |  | 2026-05-01 |  | Jade Allen Rubico | Completed
| Value Streams | Value Stream 1 (Triggers) | Diagrams | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 1 (Stages) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 1 (Outputs) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 1 (Metrics) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 2 (Triggers) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 2 (Stages) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 2 (Outputs) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 2 (Metrics) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 3 (Triggers) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 3 (Stages) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 3 (Outputs) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Value Stream 3 (Metrics) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
| TO-BE BPMN Diagrams | Core Process 1 (Swimlanes) | Diagrams | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 1 (Automated Steps) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 2 (Swimlanes) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 2 (Automated Steps) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 3 (Swimlanes) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 3 (Automated Steps) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 4 (Swimlanes) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 4 (Automated Steps) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 5 (Swimlanes) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 5 (Automated Steps) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 6 (Swimlanes) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Core Process 6 (Automated Steps) |  | 2026-05-01 |  | Jade Allen Rubico | Completed
| Stakeholder Analysis | Stakeholder Register | Table | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Concerns Matrix | Table | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | RACI Chart | Table | 2026-05-01 |  | Jade Allen Rubico | Completed
| Goal-Requirement Traceability | Goals |  | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Technical Requirements | Table | 2026-05-01 |  | Jade Allen Rubico | Completed
|  | Traceability Matrix | Table | 2026-05-01 |  | Jade Allen Rubico | Completed
4 | TO-BE Data Architecture |  | Enterprise model, polyglot, DFDs | 2026-05-01 | 2026-05-03 | Jaspher B. Alcantara | Completed | TO-BE Data Architecture completed and document uploaded.
| Enterprise Data Model | Core Entities (minimum 8) | List/Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed | TO-BE Data Architecture completed and document uploaded.
|  | ERD (Entity-Relationship Diagram) | Diagram | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Attribute Catalog | Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Business Rules | List | 2026-05-01 |  | Jaspher B. Alcantara | Completed
| Polyglot Persistence Design | Database Selection Justification |  | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Architecture Diagram | Diagram | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Data-to-Database Mapping | Diagram/Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed
| System Data Mapping | Software Table Mapping | Diagram/Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Field Mapping | Diagram/Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Gap Analysis |  | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Custom Fields | Diagram/Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed
| Data Flow Diagrams | Level 0 (Context DFD) | Diagram | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Level 1 (Decomposed DFD) | Diagram | 2026-05-01 |  | Jaspher B. Alcantara | Completed
| Data Governance | Ownership Matrix | Table | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Policies |  | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Data Quality Metrics |  | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Escalation Path | Diagram/Description | 2026-05-01 |  | Jaspher B. Alcantara | Completed
| Data Synchronization | CDC Design | Diagram | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Event Schemas | Diagram | 2026-05-01 |  | Jaspher B. Alcantara | Completed
|  | Synchronization Strategy |  | 2026-05-01 |  | Jaspher B. Alcantara | Completed
5 | TO-BE Application Architecture |  | C4 model (Levels 1-3), ADRs | 2026-05-01 | 2026-05-10 | Tom Jason D. Umali | Completed | TO-BE Application Architecture completed and document uploaded.
| Level 1: Context Diagram | System Boundaries |  | 2026-05-01 |  | Tom Jason D. Umali | Completed | TO-BE Application Architecture completed and document uploaded.
|  | User Actors (minimum 8) | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | External Systems (minimum 8) | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Data Flows | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
| Level 2: Container Diagram | Technology Containers (minimum 12) | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Communication Protocols |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Descriptions |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
| Level 3: Component Diagram | API Application Decomposition |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Layered Architecture | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Interaction Flows (minimum 3) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
| Level 4: Code (Optional) | UML Class Diagrams | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Sequence Diagrams for Critical Components | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
| Architecture Decision Records | ADR 1 (Context) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 1 (Decision) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 1 (Alternatives) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 1 (Consequences) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 2 (Context) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 2 (Decision) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 2 (Alternatives) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 2 (Consequences) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 3 (Context) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 3 (Decision) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 3 (Alternatives) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 3 (Consequences) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 4 (Context) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 4 (Decision) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 4 (Alternatives) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 4 (Consequences) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 5 (Context) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 5 (Decision) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 5 (Alternatives) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | ADR 5 (Consequences) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
| API Design | RESTful Endpoints |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | GraphQL Schema | Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Security Design | Diagram/Desc | 2026-05-01 |  | Tom Jason D. Umali | Completed
6 | TO-BE Technology Architecture |  | Deployment, stack, cost | 2026-05-01 | 2026-05-10 | Nathaniel Nazareno | Completed | TO-BE Technology Architecture completed and document uploaded.
| Deployment Architecture | Container-to-Infrastructure Mapping | Diagram | 2026-05-01 |  | Nathaniel Nazareno | Completed | TO-BE Technology Architecture completed and document uploaded.
|  | Geographic Distribution |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
| Technology Stack Matrix | Components (minimum 20) | Table | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Versions |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Justifications |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Alternatives |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
| Network Security | VPC/Subnet Design |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Security Group Rules |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Encryption Strategy | Diagram? | 2026-05-01 |  | Nathaniel Nazareno | Completed
| Scalability and HA | Scaling Strategies |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | High Availability Configuration |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | RTO/RPO |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Disaster Recovery Plan |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
| AI/ML Infrastructure | Training Pipeline |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Serving Architecture | Diagram | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Monitoring Strategy |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
| Cost Estimation | Monthly Breakdown | Table | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Annual Breakdown | Table | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Optimization Strategies | Table | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Total Cost of Ownership (TCO) | Table | 2026-05-01 |  | Nathaniel Nazareno | Completed
| Infrastructure as Code | Terraform/Pulumi Strategy |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
|  | Environment Separation |  | 2026-05-01 |  | Nathaniel Nazareno | Completed
7 | Integration Architecture |  | APIs, events, integrations | 2026-05-01 | 2026-05-17 | Tom Jason D. Umali | Completed | Integration Architecture completed and document uploaded.
| API-Led Connectivity | System APIs | Figure | 2026-05-01 |  | Tom Jason D. Umali | Completed | Integration Architecture completed and document uploaded.
|  | Process APIs | Figure | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Experience APIs | Figure | 2026-05-01 |  | Tom Jason D. Umali | Completed
| Event-Driven Architecture | Event Catalog (minimum 10 types) | Table/Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Topic Design |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Event Schemas | Table/Diagram | 2026-05-01 |  | Tom Jason D. Umali | Completed
| External System Integrations | HRIS Integration | Diagram? | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Procurement Integration | Diagram? | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Finance Integration | Diagram? | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | MDM Integration | Diagram? | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Vendor Portal Integration | Diagram? | 2026-05-01 |  | Tom Jason D. Umali | Completed
| GraphQL Integration | Schema Design |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Resolver Strategy |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Federation (if applicable) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
| Integration Testing | Contract Testing (Pact) |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
|  | Integration Test Approach |  | 2026-05-01 |  | Tom Jason D. Umali | Completed
8 | Implementation Roadmap |  | Phases, WBS, risks | May 30, 2026 | 2026-05-16 | Tom Jason D. Umali | Completed | Implementation Roadmap completed and document uploaded.
| Phased Approach | Phase 1 (Duration) | Table/Description |  |  | Tom Jason D. Umali | Completed | Implementation Roadmap completed and document uploaded.
|  | Phase 1 (Key Deliverables) |  |  |  | Tom Jason D. Umali | Completed
|  | Phase 2 (Duration) |  |  |  | Tom Jason D. Umali | Completed
|  | Phase 2 (Key Deliverables) |  |  |  | Tom Jason D. Umali | Completed
|  | Phase 3 (Duration) |  |  |  | Tom Jason D. Umali | Completed
|  | Phase 3 (Key Deliverables) |  |  |  | Tom Jason D. Umali | Completed
|  | Phase 4 (Duration) |  |  |  | Tom Jason D. Umali | Completed
|  | Phase 4 (Key Deliverables) |  |  |  | Tom Jason D. Umali | Completed
| Work Breakdown Structure | Major Tasks | Table/Description |  |  | Tom Jason D. Umali | Completed
|  | Dependencies |  |  |  | Tom Jason D. Umali | Completed
|  | Estimated Effort |  |  |  | Tom Jason D. Umali | Completed
| Resource Plan | Team Composition | Table/Description |  |  | Tom Jason D. Umali | Completed
|  | Skills Required |  |  |  | Tom Jason D. Umali | Completed
|  | Training Needs |  |  |  | Tom Jason D. Umali | Completed
| Risk Management | Key Risks |  |  |  | Tom Jason D. Umali | Completed
|  | Mitigation Strategies |  |  |  | Tom Jason D. Umali | Completed
|  | Contingency Plans |  |  |  | Tom Jason D. Umali | Completed
| Success Metrics | KPIs by Phase |  |  |  | Tom Jason D. Umali | Completed
|  | Baselines |  |  |  | Tom Jason D. Umali | Completed
|  | Targets |  |  |  | Tom Jason D. Umali | Completed
9 | Customization/Development |  | Working code, customizations |  | 2026-05-31 | All | Completed | Customization & Development code completed and pushed to repository.
| Customization Scope | Selected Software | Table |  |  | All | Completed | Customization & Development code completed and pushed to repository.
|  | Complexity Tier |  |  |  | All | Completed
|  | Customizations Implemented |  |  |  | All | Completed
| Source Code Repository | GitHub/GitLab Link | Figure |  |  | All | Completed
|  | Branch Structure | Figure |  |  | All | Completed
|  | Commit History | Figure |  |  | All | Completed
| Deployment Guide | Prerequisites |  |  |  | All | Completed
|  | Installation Steps |  |  |  | All | Completed
|  | Environment Variables |  |  |  | All | Completed
| API Documentation | Swagger/OpenAPI Link |  |  |  | All | Completed
|  | Postman Collection |  |  |  | All | Completed
| Testing Report | Unit Test Coverage |  |  |  | All | Completed
|  | Integration Test Results |  |  |  | All | Completed
|  | Known Issues |  |  |  | All | Completed
10 | System Demonstration |  | Live/recorded demo |  |  | All |  | Recorded system demonstration video completed.
| Introduction | Problem Overview |  |  |  | All |  | Recorded system demonstration video completed.
|  | Solution Overview |  |  |  | All
| Architecture Walkthrough | Key Diagrams |  |  |  | All
|  | How Diagrams Guided Implementation |  |  |  | All
| Polyglot Persistence Demo | Multiple Databases Working Together |  |  |  | All
| AI/ML Feature Demo | Model Predictions in Action |  |  |  | All
| API Demo | Endpoints via Postman |  |  |  | All
|  | Endpoints via Swagger |  |  |  | All
| Integration Demo | External System Connections |  |  |  | All
| User Interface Demo | Key User Journeys |  |  |  | All
| Conclusion | Achievements |  |  |  | All
|  | Lessons Learned |  |  |  | All
11 | Source Code & Documentation (follow outline as provided)
12 | Executive Presentation(recorded)
| 1 | Title Slide
| 2 | Executive Summary
| 3 | Company Background and Pain Points
| 4 | Solution Vision
| 5 | Business Architecture Highlights
| 6 | Data Architecture (Polyglot Persistence)
| 7 | Application Architecture (C4 Level 1 & 2)
| 8 | Application Architecture (C4 Level 3 & ADRs)
| 9 | Technology Architecture
| 10 | AI/ML Integration
| 11 | Integration Architecture
| 12 | Implementation Roadmap
| 13 | Demo Highlights
| 14 | Cost Summary and ROI
| 15 | Q&A

## Individual
# | Date of Submission (GS) | Activity | Description | Remarks | STATUS
1 | 2026-03-08 | AS-IS Business Architecture | BPMN Diagram. Current processes from high level to level 2 of critical processes not >=3 of the hypothetical company implementing SNIPE IT. | Submitted on Canvas | Completed
2 | 2026-03-15 | List of Pain Points |  | Submitted on Canvas | Completed
| 2026-03-15 | Gap Analyis |  | Submitted on Canvas | Completed
2 | 2026-03-22 | TO-BE Buiness Architecture | BPMN Diagram. Proposed or required processes from high level to level 2 of critical processes not >=3 of the hypothetical company implementing SNIPE IT. | Submitted on Canvas | Completed
3 |  | Data Architecture |  | Submitted on Canvas | Completed
| 2026-03-29 | Enterprise Data Model |  | Submitted on Canvas | Completed
| 2026-03-29 | System Data Model Mapping |  | Submitted on Canvas | Completed
| 2026-03-29 | Data Flow Diagrams (Level 0 and Level 1) |  | Submitted on Canvas | Completed
| 2026-04-12 | Data Domain Ownership Matrix |  | Submitted on Canvas | Completed
| 2026-04-12 | Data Governance Framework |  | Submitted on Canvas | Completed
| 2026-04-12 | Data Quality Assessment |  | Submitted on Canvas | Completed
| 2026-04-12 | Traceability Matrix |  | Submitted on Canvas | Completed
4 |  | Application Architecture |  | Submitted on Canvas | Completed
| 2026-04-18 | Level 1: Context Diagram | System boundaries, users, external systems | Submitted on Canvas | Completed
| 2026-04-18 | Level 2: Container Diagram | Technology containers, communication protocols | Submitted on Canvas | Completed
| 2026-04-18 | Level 3: Component Diagram | Internal structure of API container | Submitted on Canvas | Completed
| 2026-04-18 | Level 4: Code (Optional) | Detailed implementation of critical components | Submitted on Canvas | Completed
| 2026-04-25 | Architecture Decision Records (ADRs) | Key design decisions and rationale | Submitted on Canvas | Completed
| 2026-04-25 | Technology Stack Matrix | Selected technologies with justifications | Submitted on Canvas | Completed
| 2026-04-25 | Traceability Matrix | Links to pain points, processes, data architecture | Submitted on Canvas | Completed
5 |  | Tecnology Architecture |  | Submitted on Canvas | Completed
| 2026-05-03 | Deployment Architecture Diagram (Containers to Infrastructure) | Maps each C4 container to its specific cloud or on-premises infrastructure resources, including instance types, scaling configurations, and geographic placement. | Submitted on Canvas | Completed
| 2026-05-03 | Network Topology and Security Architecture | Defines network segmentation, firewall rules, security group configurations, and encryption strategies to protect data at rest and in transit across all components. | Submitted on Canvas | Completed
| 2026-05-03 | Technology Stack Selection Matrix | Documents all technology choices (languages, frameworks, databases, tools) with version specifications, justifications, and alternatives considered for each component. | Submitted on Canvas | Completed
| 2026-05-03 | Managed Services Selection and Justification | Identifies which cloud-managed services (e.g., RDS, MongoDB Atlas, SageMaker) will replace self-hosted alternatives, with cost-benefit analysis and operational overhead reduction rationale. | Submitted on Canvas | Completed
| 2026-05-03 | Infrastructure as Code Strategy (Terraform/Pulumi) | Defines how all infrastructure resources will be provisioned, versioned, and deployed using declarative IaC tools with environment separation and CI/CD integration. | Submitted on Canvas | Completed
| 2026-05-03 | Scalability and High Availability Design | Specifies auto-scaling policies, multi-zone failover configurations, RTO/RPO targets, and disaster recovery procedures for each component to meet availability SLAs. | Submitted on Canvas | Completed
| 2026-05-03 | Cost Estimation and Budget Analysis | Provides detailed monthly and annual cost projections for all cloud resources, including data transfer, storage, and compute, with optimization strategies and TCO analysis. | Submitted on Canvas | Completed
| 2026-05-03 | Traceability Matrix (Technology Decisions to Requirements) | Links every technology decision back to specific pain points, business goals, and architectural requirements to ensure justification for each choice. | Submitted on Canvas | Completed