## Sheet1
Individual Activity # | Date of Submission (GS) | Activity | Description | Link | Remarks
1 | 2026-03-08 | AS-IS Business Architecture | BPMN Diagram. Current processes from high level to level 2 of critical processes not >=3 of the hypothetical company implementing SNIPE IT. | Messenger GC
2 | 2026-03-15 | List of Pain Points
| 2026-03-15 | Gap Analyis |  | Messenger GC
2 | 2026-03-22 | TO-BE Buiness Architecture | BPMN Diagram. Proposed or required processes from high level to level 2 of critical processes not >=3 of the hypothetical company implementing SNIPE IT. | Messenger GC | Your TO BE architecture should include at the minimum the requirements stated in this project (AI, APIs, etc)
3 |  | Data Architecture |  | Messenger GC
| 2026-03-29 | Enterprise Data Model |  | Messenger GC
| 2026-03-29 | System Data Model Mapping |  | Messenger GC
| 2026-03-29 | Data Flow Diagrams (Level 0 and Level 1) |  | Messenger GC
| 2026-04-12 | Data Domain Ownership Matrix |  | Messenger GC
| 2026-04-12 | Data Governance Framework |  | Messenger GC
| 2026-04-12 | Data Quality Assessment |  | Messenger GC
| 2026-04-12 | Traceability Matrix |  | Messenger GC
4 |  | Application Architecture
| 2026-04-18 | Level 1: Context Diagram | System boundaries, users, external systems | Messenger GC | Diagram + Documentation
| 2026-04-18 | Level 2: Container Diagram | Technology containers, communication protocols | Messenger GC | Diagram + Documentation
| 2026-04-18 | Level 3: Component Diagram | Internal structure of API container | Messenger GC | Diagram + Documentation
| 2026-04-18 | Level 4: Code (Optional) | Detailed implementation of critical components | Messenger GC | UML/ER Diagrams
| 2026-04-25 | Architecture Decision Records (ADRs) | Key design decisions and rationale | Messenger GC | Document
| 2026-04-25 | Technology Stack Matrix | Selected technologies with justifications | Messenger GC | Spreadsheet
| 2026-04-25 | Traceability Matrix | Links to pain points, processes, data architecture | Messenger GC | Spreadsheet
5 |  | Tecnology Architecture
| 2026-05-03 | Deployment Architecture Diagram (Containers to Infrastructure) | Maps each C4 container to its specific cloud or on-premises infrastructure resources, including instance types, scaling configurations, and geographic placement. | Messenger GC | Diagram
| 2026-05-03 | Network Topology and Security Architecture | Defines network segmentation, firewall rules, security group configurations, and encryption strategies to protect data at rest and in transit across all components. | Messenger GC | Diagram + Documentation
| 2026-05-03 | Technology Stack Selection Matrix | Documents all technology choices (languages, frameworks, databases, tools) with version specifications, justifications, and alternatives considered for each component. | Messenger GC | Spreadsheet
| 2026-05-03 | Managed Services Selection and Justification | Identifies which cloud-managed services (e.g., RDS, MongoDB Atlas, SageMaker) will replace self-hosted alternatives, with cost-benefit analysis and operational overhead reduction rationale. | Messenger GC | Documentation
| 2026-05-03 | Infrastructure as Code Strategy (Terraform/Pulumi) | Defines how all infrastructure resources will be provisioned, versioned, and deployed using declarative IaC tools with environment separation and CI/CD integration. | Messenger GC | Documentation + Code Files
| 2026-05-03 | Scalability and High Availability Design | Specifies auto-scaling policies, multi-zone failover configurations, RTO/RPO targets, and disaster recovery procedures for each component to meet availability SLAs. | Messenger GC | Documentation
| 2026-05-03 | Cost Estimation and Budget Analysis | Provides detailed monthly and annual cost projections for all cloud resources, including data transfer, storage, and compute, with optimization strategies and TCO analysis. | Messenger GC | Spreadsheet
| 2026-05-03 | Traceability Matrix (Technology Decisions to Requirements) | Links every technology decision back to specific pain points, business goals, and architectural requirements to ensure justification for each choice. | Messenger GC | Spreadsheet

## Group
Deliverable | Weight | Due | Description
Project Proposal | 5% | 2026-04-26 | Approval document
Company Background | 5% | 2026-04-26 | Profile, AS-IS, business case
TO-BE Business Architecture | 10% | 2026-05-03 | Capabilities, value streams, BPMN
TO-BE Data Architecture | 10% | 2026-05-03 | Enterprise model, polyglot, DFDs
TO-BE Application Architecture | 10% | 2026-05-10 | C4 model (Levels 1-3), ADRs
TO-BE Technology Architecture | 10% | 2026-05-10 | Deployment, stack, cost
Integration Architecture | 5% | 2026-05-17 | APIs, events, integrations
Implementation Roadmap | 5% | 2026-05-16 | Phases, WBS, risks
Customization/Development | 15% | 2026-05-31 | Working code, customizations
System Demonstration | 15% | 2026-06-07 | Live/recorded demo
Source Code & Documentation (follow outline as provided) | 5% | 2026-06-14 | GitHub, deployment guide
Executive Presentation(recorded) | 5% | 2026-06-20 | 12-15 slide deck